## Slide 1: SAS Exit Strategy
What runs on SAS, how critical it is, and how we get off it
1
Inventory use cases
2
Assess criticality
3
Confirm exit paths
4
Migrate or retire
5
Decommission SAS

## Slide 2: Our Goal: A Complete, Low-Risk Exit from SAS
SUMMARY
The Goal
Remove every Corporate Risk dependency on SAS and fully exit the platform, without disrupting critical risk processes.
Why Now
Given SAS contract concerns, leadership has asked us to plan a full exit. Corporate Risk is the largest SAS user, so we lead the assessment of timeline and effort.
Key Questions
What runs on SAS and how critical is it? Does each use case have an exit strategy, and when? If not, who must build one?
The Approach
Track 1 inventories, prioritizes and exits each use case. Track 2 cleans up unused storage and access to cut cost while we exit.
The Payoff
No SAS dependency risk at the end. Along the way, an estimated 550,074 GB (~$1.6M a year) of storage savings, once validated.
THE THREE QUESTIONS WE MUST ANSWER
1 What runs on SAS?
Use cases, owners and criticality
What each use case does, who relies on it, and what breaks if it stops.
2 Is there an exit plan?
If yes: where it moves, and when
A named target, owner, effort and date, sequenced by criticality.
3 If not, who builds it?
The right people in the room
Business owner, SAS platform, architecture and Controls agree a path and date.

## Slide 3: Every SAS Use Case Needs an Exit Path, a Date and an Owner
THE EXIT QUESTIONS
START
Each SAS use case in the inventory
QUESTION 1
What does it do, and how critical is it?
Owner, purpose, data in and out, who relies on it, criticality tier
QUESTION 2
Is there an exit strategy?
A named target platform, owner, effort and timeline
Yes
YES · CONFIRM WHEN
Lock the date and the effort
Agree the target, migration effort, dependencies and a fallback; add it to an exit wave.
Not needed
No
NOT NEEDED · RETIRE
Archive it and switch it off
Inactive, obsolete or duplicated work: keep only what retention rules require, then shut it down.
NO · BUILD ONE
Get the right people in the room
Business owner, SAS platform team, target architecture, Finance and Controls agree a target, owner and date.
THEN · EXECUTE THE EXIT
Migrate, test, cut over, decommission
Build and parallel-run on the target, switch over, then remove SAS jobs, access and storage.
What counts as an exit strategy: a named target platform, an accountable owner, an effort estimate, a timeline with dependencies, and a fallback if the date slips.
Outcome: one exit register showing every SAS use case with its owner, criticality, exit path, target date and blockers.

## Slide 4: Each Use Case Lands in One of Five Exit Statuses
EXIT STATUS
STATUS
WHAT IT MEANS
WHAT HAPPENS NEXT
EXIT CONFIRMED
Target platform, owner and date are agreed; effort and dependencies are understood.
Schedule into an exit wave and track to the date.
PATH KNOWN · NO DATE
A likely target exists, but timeline, funding or capacity is not confirmed.
Confirm effort, funding and a date with the target-platform owner.
NO EXIT STRATEGY
No viable target yet, or the logic is tightly tied to SAS.
Convene the owner, SAS platform, architecture and Controls to design one.
RETIRE
Inactive, obsolete or duplicated; nothing downstream depends on it.
Confirm retention, archive what must be kept, then shut it down.
OWNER UNKNOWN
No confirmed owner, or its purpose and consumers are not documented.
Trace the owner through job logs and access lists; escalate if unclaimed.
Leadership readout: the number of use cases in each status, critical (T1/T2) first, with target dates and blockers.

## Slide 5: Criticality Sets the Order and the Care of Each Exit
PRIORITIZATION
TIER
WHAT IT COVERS
HOW WE EXIT
T1 CRITICAL
Regulatory filings, capital and allowance, production risk models, material reporting and decisions, daily monitoring, key controls and deadline-driven pipelines
Plan first: executive visibility, a full dependency map and a fallback. Prove a tested replacement with clear service levels in a parallel run before cutover.
T2 MEDIUM
Recurring analytics, internal reporting and analytical data preparation
Migrate or consolidate in waves, based on target readiness and value.
T3 LOW
Ad hoc, inactive, obsolete or duplicated work
Retire or archive once retention and dependencies are confirmed.
Why not rank by storage use? Low usage is not low importance: a quarterly regulatory job can sit idle for weeks and still be critical.
Override rule: any regulatory or controlled workload gets executive review, regardless of usage or savings.

## Slide 6: Two Connected Tracks: Exit First, Clean Up Along the Way
APPROACH
Program goal: know what runs on SAS, why it matters, and how and when each use case exits.
TRACK 1 · PRIMARY
Use-Case Exit Readiness
Map each workspace to its use cases and business outcomes
Assess criticality, dependencies and controls
Confirm an exit path, target date and owner for each use case
Group exits into funded, owned migration waves
Decommission SAS once each wave is verified
OUTPUT Exit register, timeline and migration waves
TRACK 2 · SUPPORTING
Storage & Access Clean-Up
Validate empty (0%) and low-use (under 60%) storage allocations
Right-size or consolidate approved allocations
Remove access that is no longer needed, as a separate step
Confirm de-allocation and the billing impact
OUTPUT Lower run cost and a smaller footprint to migrate
How they connect: clean-up findings feed the exit plan. Unused storage often points to use cases we can retire instead of migrate.
Guardrail: nothing is retired or reduced only because usage looks low. Owners first confirm purpose, seasonality, retention and downstream consumers.

## Slide 7: From Inventory to Decommission: Five Steps for Every Use Case
EXIT FLOW
EXIT READINESS · STEPS 1–4
THE PAYOFF
1
Baseline
Confirm every workspace, owner, environment, user, storage allocation and recent activity.
GATE
Inventory reconciled to platform data
2
Discover
Document what each use case does: purpose, sources, jobs, outputs, consumers and run calendar.
GATE
Owner has confirmed the use case
3
Assess
Rate criticality and map regulatory, model and control obligations and dependencies.
GATE
Criticality tier agreed
4
Decide
Pick the exit path: migrate, consolidate, replace, retire, or retain briefly with an end date.
GATE
Target, owner and date approved
5
Execute & Exit
Build and parallel-run on the target, cut over, then remove SAS jobs, access and storage.
THEN
SAS dependency removed and verified
Decision gate: a use case moves to execution only when its owner, criticality, dependencies, target readiness and control evidence are understood.

## Slide 8: Who Needs to Be in the Room to Build Each Exit Strategy
OPERATING MODEL
Executive sponsor
Technology leadership
Sets urgency and the exit deadline; decides exit-versus-retain trade-offs; clears cross-team blockers.
Corporate Risk program lead
Accountable owner
Owns the consolidated use-case review and recommends an exit path for each use case.
Data management PMO
Program office
Mobilizes owners, runs the exit register and tracker, keeps evidence and escalates delays.
SAS platform team
Technology
Provides inventories, job logs and dependencies; makes allocation changes and shuts down workloads.
Business, model and report owners
Use-case owners
Confirm purpose, criticality and downstream impact; accept the target and sign off cutover.
Architecture, Finance and Controls
Target and oversight
Approve target platforms, cost, data sourcing, retention, security, and model and report controls.
No exit strategy yet? The business owner, SAS platform team, target architecture and Controls meet together to agree a target, an owner and a date.
Immediate decision: name the accountable Corporate Risk program lead and a target-platform owner for each exit path.

## Slide 9: Storage Clean-Up Lowers Cost While We Exit
SUPPORTING TRACK
550,074 GB
Potential storage reduction
Allocations that are empty or under 60% used
~$1.6M
Potential annual savings
Annualized using the platform team’s storage cost estimate
<60%
Utilization threshold
Below this, an allocation is reviewed; owners confirm headroom first
4×
Storage footprint factor
Each allocated GB also carries snapshot and business-continuity copies
HOW SAVINGS BECOME REAL
1
Identify
Empty and low-use allocations; owners with several workspaces
2
Validate
Business use, peak cycles, jobs, outputs and retention
3
Approve
Owner signs off a target size with room to grow
4
Reduce
Archive or delete approved data; platform releases storage
5
Verify
Smaller allocation and billing impact confirmed
HOW TO POSITION THE NUMBER
An opportunity estimate, not realized savings: it counts only after owner review, dependency checks, approved allocation changes and confirmed billing impact.
Excel model: supports workspace-level sizing and scenarios; the 550,074 GB figure remains the leadership baseline.

## Slide 10: How We Run It: Cadence and Decision Products
GOVERNANCE
FORUM
WHAT WE COVER
OUTPUT
Twice-weekly working session
Program team, owners, platform
Owner outreach, unknown workloads, platform questions, dependencies and issues.
Updated exit register and issue log
Weekly leadership readout
Program lead to sponsor
Use cases mapped, critical exposures, exit status, storage progress and blockers.
One-page status for leadership
Biweekly architecture review
Architecture, platform, target owners
Target platforms, shared migration patterns, data sourcing and control dependencies.
Approved exit paths and patterns
Monthly steering
Executive sponsor and leads
Exit waves, funding, exceptions, SAS contract decisions and realized savings.
Decisions and escalations recorded
Core dashboard: use cases mapped • criticality • exit status • target dates • T1/T2 exposure • GB approved to reclaim • realized savings • blockers

## Slide 11: First 30 Business Days: Tangible Outputs
MOBILIZATION
WEEKS 1–2
Baseline & Control
Confirm scope, decision makers and the escalation route
Reconcile workspace, owner, user and platform data
Collect job and run history; flag unknown workloads
Stand up the exit register and the weekly leadership readout
WEEKS 3–4
Discovery & Priority
Send a standard use-case intake to every owner
Triage critical (T1/T2) workloads and the largest storage users first
Map sources, outputs, consumers and control obligations
Start exit-strategy sessions for critical use cases that have none
WEEKS 5–6
Decision & Action
Give each use case an exit status and target readiness
Agree how de-allocation and access removal will work
Propose the first exit wave and its target-platform owners
Publish the first steering pack with blockers and asks
LEADERSHIP OUTPUT
at day 30
Every in-scope use case with an owner, criticality tier and exit status
The list of use cases with no exit strategy, and who must build each one
Draft exit waves and timeline, plus validated storage and access actions

## Slide 12: What We Need From Leadership Now
LEADERSHIP DECISIONS
1
Confirm the mandate and timeline
NEEDED FIRST
Full SAS exit as the goal; which environments are in scope; the target exit date; and what counts as an acceptable exit strategy.
2
Name accountable leaders
NEEDED FIRST
Corporate Risk program lead, technology platform lead, Finance/FinOps partner and the escalation route.
3
Approve how we prioritize
Criticality and target readiness set the order; storage savings inform but do not drive it.
4
Authorize owner outreach
Standard intake to every workspace owner; focused discovery for critical (T0/T1) and the largest workloads.
5
Unblock execution
Confirm the processes for archive and deletion, allocation reduction, access removal and savings evidence.
Recommended approval: proceed with the exit-led program, and use 550,074 GB / ~$1.6M as the current storage-savings baseline.

## Slide 13: Appendix
Key terms used in this deck

## Slide 14: Key Terms Used in This Deck
APPENDIX
SAS use case
A business process that runs on SAS, such as a model, report or data job, with an owner and consumers.
Exit strategy
A named target platform, owner, effort estimate, timeline and fallback for moving one use case off SAS.
Workspace
A SAS project area with its own storage, users and jobs; one use case can span several.
Exit status
Where a use case stands: confirmed, path known with no date, no strategy, retire, or owner unknown.
Criticality tier
T1 (critical) to T3 (low): the business impact if the use case stopped working.
Disposition
The decision for a use case: migrate, consolidate, replace, retire, or retain briefly with an end date.
Allocation
Storage reserved for a workspace. Utilization is the share of it actually used.
De-allocation
The platform team releases reserved storage so it is no longer billed.
Entitlement
A person’s access to a workspace; removing unused access lowers risk and cost.
Parallel run
Running SAS and the new platform side by side to prove matching results before cutover.