## Slide 1: SAS Storage & Entitlement Reduction
Three pieces: storage first, then entitlements, then the overlap
1
Storage allocation
2
Entitlements
3
Overlap
Notes: For discussion with Jacqueline, Tuesday October 20 (about 2:30, not yet on calendar). Kevin's ask: thoughts on how we would approach reducing SAS cost and how we would do it. This is a plan; numbers marked TBD are being pulled.

## Slide 2: Cutting SAS Costs: Storage First, Then Entitlements
SUMMARY
The Ask
Show Jacqueline how we would reduce SAS cost: what to cut, in what order, and how.
Cost Driver
Allocated storage, not used storage, drives the bill, and each active GB carries about a 4× footprint.
How Access Works
An entitlement is a license to the SAS platform, not to one workspace. Storage sits in workspaces, each with an owner.
Approach
Three pieces: lower storage allocation, remove entitlements no one needs, then clean up the overlap. Storage first; not all at once.
Running It
Work through 64 workspace owners with CDO support, starting with 0% utilization workspaces.
BY THE NUMBERS
~1.3 PB
Storage allocated
About 1.3M GB across SAS workspaces.
166 / 64
Workspaces / unique owners
Many owners hold several workspaces.
~1,200
Entitled users in IT&V
About half of corporate risk SAS entitlements; to confirm.
Notes: One-page overview. "SaaS" in our notes means the SAS platform. Storage allocation is the priority because each active GB carries about a 4x footprint. The entitlement count for IT&V (~1,200, about half of corporate risk SAS entitlements) was stated from memory in the meeting; confirm the figure and the group name.

## Slide 3: Allocated Storage, Not Usage, Drives the Cost
COST DRIVERS
~1.3 PB
Storage allocated
About 1.3M GB across SAS workspaces
$60K
Per PB, per month
About $720K per PB per year
~$0.94M
Implied annual cost
1.3 PB × $720K, allocation only
4×
Impact per active GB
25 GB active ≈ 100 GB total footprint
Why it matters: we pay for what is allocated, not what is used, and most owners use a small fraction of their allocation.
Source: SAS workspace reporting footnote (Confluence). On-prem allocation cost only; all figures to be validated.
Notes: Footnote rate: ~$60K/month per 1 PB (~1M GB), so ~$720K/yr. We have ~1.3M GB allocated, so allocation alone is a little under $1M/yr. The earlier $27M figure covered much more than SAS and is not comparable. The existing deck (slide 3) says active storage has a 4x impact.

## Slide 4: The 4× Multiplier Likely Explains the $1.6M Savings Estimate
COST DRIVERS
SAVINGS FROM FREEING ~550K GB ($M / YR)
Chart: 
| At base rate | With 4× impact
Savings | 0.4 | 1.58
HOW THE NUMBERS RECONCILE
Bringing every owner below 60% utilization frees about 550K GB
At the $720K per PB rate, that is only about $0.40M a year
Applying the 4× impact gives about $1.58M, in line with the ~$1.6M on the savings slide
If 4× applies to the full allocation, the true run-rate is higher than the ~$0.94M the footnote implies
TO CONFIRM
How SAS billing applies the 4×, and what we are actually charged today.
Notes: Working hypothesis for the "hidden cost": 550K GB = 0.55 PB × $720K ≈ $396K; × 4 ≈ $1.58M, which matches the ~$1.6M on the savings slide. We do not have visibility into actual billing, so this needs confirmation.

## Slide 5: Entitlements Are Platform-Wide; Storage Lives in Workspaces
HOW IT WORKS
SAS ENTITLEMENT License to the platform: any entitled user can reach any workspace
Workspace A
Owner A
Allocated vs used
10 files
Workspace B
Owner B
Allocated vs used
10 files
Workspace C
Owner A
Allocated vs used
1 file
CONSOLIDATE
Move C's one file into A and retire C. Its whole allocation comes off the bill; no one loses access.
WHAT THIS MEANS
Entitlements and storage are two separate populations to reduce
One owner can hold several workspaces: 166 workspaces sit with 64 owners
We pay for each workspace's allocation, whether it holds 10 files or one
CASE IN POINT
A user's entitlement was removed, but his workspace still holds allocated storage. Removing access alone does not cut storage cost.
Notes: Analogy from the meeting: an entitlement is like an application license. You install SAS, get the license, then connect to whichever workspace you need. Example: Kevin owns one workspace and Brian owns another; everyone on the team is entitled and can reach either. If a third workspace holds one file, moving that file into one of the others lets us retire the third workspace and its allocation. Case in point for entitlement vs storage: Ben's entitlement was removed but his workspace still holds allocated storage.

## Slide 6: Three Pieces, Storage First
APPROACH
1
Storage Allocation
Priority 1
WHAT
Eliminate 0% utilization workspaces, consolidate owners with several workspaces, and cut oversized allocations.
WHY
The biggest cost lever: each active GB carries about a 4× footprint.
2
Entitlements
Priority 2
WHAT
Remove SAS access for users who don't need it, starting with groups that hold no storage and heavily entitled groups.
WHY
A separate population; cuts access risk and any per-user cost, not storage.
3
Overlap
Later
WHAT
People who are both owners and users, or who moved roles and no longer need a workspace or access.
WHY
Hard to identify up front; becomes clearer as pieces 1 and 2 progress.
Sequencing: storage first, then entitlements. Running both at once would be too disruptive for owners and users.
Notes: Storage allocation is the priority because of the 4x ratio: every GB removed is worth about four. Entitlements are a separate population, and IT&V holds about half of corporate risk SAS entitlements. The overlap (owners who are also users, people who moved roles) is real but hard to identify from the start. Doing storage and entitlements at the same time felt too drastic.

## Slide 7: Storage Allocation: Work Through It Workspace by Workspace
PIECE 1 · STORAGE ALLOCATION
1
Eliminate 0% Workspaces
Remove or archive workspaces with no usage; their full allocation comes off the bill.
SIZING TBD workspaces · TBD GB · $TBD/yr
›
2
Consolidate
Owners with several workspaces merge into fewer, sized to what they actually use.
SIZING TBD workspaces · TBD GB · $TBD/yr
›
3
Right-Size the Rest
Cut allocation toward actual use plus headroom, tier by tier (next slide).
SIZING TBD workspaces · TBD GB · $TBD/yr
EXAMPLE · CONSOLIDATE
One owner holds about 202K GB across several workspaces and uses about 80K. He keeps his access; his storage shrinks.
EXAMPLE · ELIMINATE
A single unused workspace of about 14K GB could be retired, taking its whole allocation off the bill.
HOW IT GETS DONE: workspace owners work with the CDO team to clean up, archive old files, and follow storage best practices.
Notes: Consolidation example: Chong Lee holds about 202,000 GB across several workspaces and uses about 80,000; he still needs his entitlement, but his workspaces can be consolidated and right-sized. Elimination example: a single unused workspace of about 14,000 GB could come off entirely. Existing deck recommendation: workspace owners work with the CDO team to clean up their environment, archive old files, and follow best practices. Sizing numbers to come from Jake.

## Slide 8: Storage Tiers: Remove, Reduce, or Right-Size by Usage
PIECE 1 · STORAGE ALLOCATION
Low Use
Remove
About 0–10% of allocation used
ACTION
Start with 0% utilization workspaces
Scrutinize every owner: why do they need this?
Move any needed data to an owner closer to it
Middle
Reduce
Meaningful but partial use
ACTION
Cut allocation toward actual use plus reasonable headroom
Confirm what still feeds downstream models or reports
Top
Right-size
Heavy users with a real need
ACTION
Confirm continued need and trim where possible (e.g. 11,000 → 10,000 GB)
Absorb smaller owners' data where it fits
Educate on keeping usage in line with allocation
EXAMPLE: one owner holds about 34K GB of allocation and uses under 8% of it.
Notes: Every little bit adds up, even small trims on large allocations. The example is Kelsey (~34,000 GB, <8% used); Kelsey and John work in tandem, so meet with them together. Another example: Kyle Lewis holds about 800 GB and has since changed teams.

## Slide 9: First Move: 0% Utilization Workspaces
PIECE 1 · STATUS
0% Utilization Workspaces
Scope: TBD workspaces · TBD GB allocated · 64 workspace owners overall · Lead: to be named
OVERALL
AMBER
SUMMARY
Workspaces with no usage are the cleanest first cut: remove or archive them and their allocation comes off the bill.
PROGRESS SO FAR
Storage view built per workspace (allocated vs used)
166 workspaces mapped to 64 unique owners
0% utilization workspaces identified for review
KEY STEPS AND DUE DATES
Pivot workspaces by owner; size the 0% set · in progress
Agree with Jacqueline how to engage the 64 owners · 10/20
Owners designate contacts to clean up with CDO · TBD
BLOCKERS AND RISKS
No confirmed way yet to de-allocate storage
64 owners is a lot to engage one by one
Owners may need time and direction to archive data
NEXT: PIECE 2 · ENTITLEMENTS · start with no-storage groups once bulk removal is available
NOT STARTED
Notes: 166 workspaces map to 64 unique owners because many owners hold several workspaces. Open question for Jacqueline: do we meet every owner, or have each designate someone savvy to work with us and the CDO team on cleanup? Jake is building the pivot of workspaces by owner and sizing the 0% set.

## Slide 10: Entitlements: Remove Access No One Needs
PIECE 2 · ENTITLEMENTS
WHERE TO START
No-storage groups
Quick win
~46 users in risk groups where no one holds allocated storage (as of 5/29)
IT&V
Largest
About 1,200 entitled users, roughly half of corporate risk SAS entitlements
MRM
Low activity
233 entitled users, only 36 active
Default: if no one in your group holds storage, you likely don't need an entitlement. Exceptions (e.g., pulling from another LOB) can request it back.
HOW IT RUNS
Bulk Removal, Q4 2026
A bulk entitlement removal process is in development. We start after storage is underway so the two efforts don't collide.
KEEP IN MIND
Access Is Not Storage
Entitlements are platform-wide, so this piece cuts access and any per-user cost, not workspace allocation.
Notes: The no-storage group: about 46 users (5/29 data) sit in risk groups where no one holds allocated storage; they may pull from another LOB, but the default is to remove. IT&V: about 1,200 entitled users, roughly half of corporate risk SAS entitlements (figure and group name to confirm). MRM: 233 entitled, 36 active.

## Slide 11: The Overlap: Owners, Users, and Role Changes
PIECE 3 · OVERLAP
A
Owner and User
Someone can own workspaces and hold an entitlement. Consolidating their storage may not change their access, and that's fine.
B
Moved Roles
People who left a role may no longer need a workspace or an entitlement, e.g., an owner who changed teams still holds about 800 GB.
C
Team-Wide Access
Whole teams are entitled while one manager owns the workspace. Keep one accountable owner; others route through them.
WHY LATER
This overlap is hard to identify up front. HR data and the owner conversations in pieces 1 and 2 will surface most of it.
LATER
Notes: Examples: Chong Lee is both an owner and an entitled user; consolidating his storage doesn't remove his access. Kyle Lewis moved out of Y14 and still holds about 800 GB. Sean Douglas's whole team (e.g. Philip Taft) is entitled while only Sean owns the workspace. Thomas (PyForm AVO) owns a small allocation that likely belongs with someone closer to the model. History: Leopold once owned all SAS workspaces, then pushed them to individual RMG owners because he couldn't speak to the contents.

## Slide 12: Open Questions to Resolve Before We Execute
OPEN QUESTIONS
1
Blocker
How do we de-allocate storage once a workspace is cleared?
No one on the email thread knows the mechanism; SAS contract concerns raised.
2
Can 0% workspaces be deleted outright?
Or do they need to be archived first, and by whom?
3
How do we engage 64 owners?
Meet each one, or have owners designate someone to work with us and CDO?
4
What is the licensing model?
Per-user vs enterprise decides whether removing users saves money directly.
5
What are we actually charged?
Does the 4× apply in billing? Allocation vs total run-rate.
6
Is the inactive-user report complete?
It shows far fewer inactive users than expected.
Notes: The first question is the blocker: nothing executes until we know how to de-allocate storage and remove entitlements.

## Slide 13: Next Steps
NEXT STEPS
Action | Owner | When / notes
Present the three-piece approach to Jacqueline | Kelly | Tue 10/20, ~2:30 (not yet on calendar)
Pivot workspaces by owner; size 0% workspaces in GB and $ | Jake | In progress
Size savings per piece using the $/PB rate and 4× factor | Jake | Before the detailed review
Refresh entitlement and workspace data from live reports | Kelly | Replaces the 5/29 snapshot
Meet the bulk entitlement removal process owner | Jake, Kelly | This week; process ETA Q4 2026
Owner breakouts: Chong Lee; Leopold; Kelsey & John; Sean Douglas; Thomas; Maxim | Jake, Kelly | Next 2 weeks
Engage model governance and the CDO team on cleanup | Jake, Kelly | Natalie's team; CDO
Confirm the licensing model and how billing applies 4× | TBD | Open question
Notes: Ask for Jacqueline: agreement on the three-piece approach with storage first, guidance on engaging the 64 owners, and help unblocking the de-allocation mechanism.